Begin this 18-24 months prior to desired NT typesetting date[1]
Items should be processed in the order listed
[1] If you are doing your own typesetting and are self funding this printing you do not need to begin the process 18-24 months in advance. Depending on the pictures you use, this form could be started and completed in a week.
RAD Approval
Based on discussion with the team, I support their decision to publish. The team has filed with me and the ADAA a brief paragraph describing their distribution plans for this publication, and where undistributed copies will be stored, etc.
RAD approval to publish: ___________________________________ Date: ______________
Information to be filled out by language team:
Language Team: ____________________________________________________________________
Language Name: _______________________________	ISO Code: ________
Vernacular Title: ______________________________________________________
English Translation of Title: ________________________________________________________
Language group population: __________Number of language group copies: ___________
Names of all translators involved (for bibliography): _______________________________________
__________________________________________________________________________________
ADAA verification of project progress
1. Orthography status:	 Trial	 Working	 Established
2. Grammar status:	 In progress	 Advanced	 Completed
3. Percentage previously published:	OT: _________	NT: __________
4. Program in sync with Program Plan:	 Yes	 No
## ADAA comment: ___________________________________________________________________
## Signature _____________________________________________ Date: _______________________

ADAA approval (needed if applying for funding or publishing a diglot)
Name underwriter (TBL, BS, private) applied to: ___________________________________
     If privately funded, whom will you list as publisher? (Do not list SIL.): __________________
If requesting a diglot, submit written rationale to ADAA for recommendation and approval (approved under extraordinary circumstances only).
ADAA approval for Diglot: _________________________
Permission to print obtained from publisher of non-vernacular version? Yes ____	No _____

ADAA approval: _____________________________________________ Date: _________________
Schedule Typesetting Date with Scripture Publications Coordinator (SPC)
1. Date scheduled: _________ (This should be 6-12 months in advance.)
2. Pick up a copy of the Publication Guidelines, as set forth by International Publishing Services (IPUB), SIL, Dallas. Any deviation from the guidelines should be approved by IPUB, regardless of the source of funding. This is to ensure that all SIL publications meet certain quality criteria.

Project Funding Coordinator (PFC)
 TBL: I have read and familiarized myself with the Publication Guidelines set by IPUB. I realize that the funding agency I have applied to may refuse to pay for any part of a publication which falls outside of the guidelines (e.g. larger point size, more footnotes, references done in margins, plastic covers, gold-edging), and I am prepared to pay for anything that will not be covered. Thus I release TBL, BS and SIL/MSEAG from all financial obligations for anything done outside of these guidelines.
 TBS: I realize I am responsible to follow their publication guidelines.
 MBS: I realize I am responsible to follow their publication guidelines.
##### OR
 Private Funding: I realize that private funding arrangements do not always go as planned (i.e. there may be charges that were not originally planned for or people may commit to funding a project and then not be able to follow through with their commitment). I therefore release SIL/MSEAG from all financial obligations for any expenses that the private donor will not be able to cover, and agree to pay for them myself.

## Team’s signature: _______________________________________ Date: ________________
        (Signature indicates agreement with one of the two statements above, please check one.)
## Account number for all publication costs: _________-________________
## Account Name: ________________________________________
 Underwriter approval obtained. Name of underwriter: _____________________________

Steps to complete with SPC
(6 months before NT typesetting date)
1. 	Select black & white illustrations and fill out picture list form.
2. 	Fill out DC Cook permission slip if you choose Cook illustrations.
3. 	Select and make a mockup of color illustrations.
4. 	If desired, ask and arrange for any new drawings.
5. 	Submit the cover design to typesetter to be completed.
6. 	Select maps, translate & insert place names; submit to typesetter.
7. 	Self-typesetters only: Submit cover, title, and verso pages to SPC for approval.
8. Number of PR copies: __________. (to be determined and distributed by SPC)
9. Total of language group & PR copies: ___________

## SPC approval: ________________________________________ Date: _________________

Translation Coordinator Consultant Check Verification
(1-4 months before typesetting)
1. 	New Testament all consultant checked OR  will be before typesetting date.
2. Optional supplementary material must be consultant checked, except material from a previously approved template or publication, such as the standard topical index or glossary available from the Translation Coord.
	Consultant checked	Not included in Publication	Standard/Template
Introduction – up to ½ page			
Section Headings			
Parallel Passage References			
Cross References			
Footnotes			
Glossary – up to 20 pp.			
Topical Index – up to 8 pp.			

## Translation Coordinator comment: _____________________________________________________
## Signature: ______________________________________________________ Date: _____________

ADAA final verification of project progress
(before NT typesetting date)
Academic requirements previously in progress have been completed: Yes 	No 

Signature: ______________________________________________________ Date: _____________